## Project Backlog G6
Group 6 - ROOTSHELL | Network Security Assessment of Cloud Network Architecture
Role | Responsibility | Assigned to | Sprint Start Date | Sprint End Date
Product Owner | Defines WHAT to build, prioritizes backlog, represents stakeholders. | Shubham | 2026-01-24 | 2026-02-14
Scrum Master | Facilitates process, removes blockers, coaches the team, Captures Stand Up meeting Notes | Ojas
Dev team | Self-organizing, cross-functional, delivers the increment | All
Task | Sub Task | Assigned to | Assignment Date | Due Date | Status | Status Change Comment Log | Date of Completion
Creating Github |  | Ojas | 2026-01-21 | 2026-01-26 | Done | 21-01 Ojas sent invite to all | 2026-01-27
| Add team members | Ojas | 2026-01-21 | 2026-01-26 | Done |  | 2026-01-27
| Check upload/edit functions | All | 2026-01-21 | 2026-01-26 | Done | 27-01 All other members confirmed | 2026-01-27
Updating in the Meeting Log | Daily Update capture | Ojas | 2026-01-24 | 2026-02-14 | Done | Ojas is updating every alternate day | 2026-02-14
Setting Up meet |  | Ojas | 2026-01-24 | 2026-02-14 | Done | 28-01: Due meeting notes issue in place of original google meets, Zoom is decided to be used. Ojas Created daily zoom link | 2026-02-14
Setting up Sprint Time line and Sprint Backlog Doc |  | Sachin | 2026-01-24 | 2026-02-14 | Done | 29-01 Sachin has requested the exentsion till 4th. Akash told in the class that we can submit till 4-Feb | 2026-02-14
Creation of the Project Backlog |  | Sachin | 2026-01-28 | 2026-02-08 | Done |  | 2026-02-14
Network Architecture Review | AI-assisted research, gather sources, outline | Ojas | 2026-01-28 | 2026-01-30 | Done |  | 2026-01-30
| Write sections, create visuals, review | Ojas | 2026-01-28 | 2026-01-30 | Done | 30-01 Ojas has completed his part and uploaded his part | 2026-01-30
| Upload Prompt in Prompt folder | Ojas | 2026-01-28 | 2026-01-31 | Done |  | 2026-02-01
| Peer review | Shubham | 2026-01-28 | 2026-02-01 | Done |  | 2026-02-03
Vulnerability Identification Report | AI-assisted research, gather sources, outline | Shubham | 2026-01-28 | 2026-01-30 | Done |  | 2026-01-30
| Write sections, create visuals, complete report -Review | Shubham | 2026-01-28 | 2026-01-30 | Done |  | 2026-01-30
| Upload Prompt in Prompt folder | Shubham | 2026-01-28 | 2026-01-31 | Done |  | 2026-02-01
| Peer review | Ojas | 2026-01-28 | 2026-02-01 | Done |  | 2026-02-03
Best Practice Comparison | AI-assisted research, gather sources, outline | Nigam | 2026-01-28 | 2026-01-30 | Done | 29-01: Nigam confirmed AI research - part over | 2026-01-30
| Write sections, create visuals, review | Nigam | 2026-01-28 | 2026-01-30 | Done | 29-01: Nigam is starting now the report part. Uploaded the same. 30-01: Nigam has created report on overall basis. | 2026-01-30
| Upload Prompt in Prompt folder | Nigam | 2026-01-28 | 2026-01-31 | Done | 29-01 Nigam prompts are ready. | 2026-02-01
| Peer review | Sachin | 2026-01-28 | 2026-02-01 | Done |  | 2026-02-03
Threat Scenario Analysis | AI-assisted research, gather sources, outline | Sachin | 2026-01-28 | 2026-01-30 | Done | 29-01 Sachin has identified few prompts, completed AI research,building the outline now. 30-01Completed threat analysis outline. | 2026-01-30
| Write sections, create visuals, review | Sachin | 2026-01-28 | 2026-01-30 | Done | 30-01 need to modify report in line with Network Architecture considered by Ojas | 2026-01-30
| Upload Prompt in Prompt folder | Sachin | 2026-01-28 | 2026-01-31 | Done |  | 2026-02-01
| Peer review | Ojas | 2026-01-28 | 2026-02-01 | Done |  | 2026-02-03
Improvement Recommendations | AI-assisted research, gather sources, outline | All | 2026-01-30 | 2026-02-01 | Done | 31-01-2026 Sachin/Nigam's report/outline has improvement suggestions | 2026-02-01
| Write sections, create visuals, review | All | 2026-01-30 | 2026-02-01 | Done |  | 2026-02-01
| Peer review | All | 2026-02-02 | 2026-02-02 | Done |  | 2026-02-03
Executive Summary | Prepare final report | Sachin | 2026-02-04 | 2026-02-06 | Done |  | 2026-02-07
| Team Review and checklist for the project | All | 2026-02-04 | 2026-02-06 | Done |  | 2026-02-07
| Checklist review, finalization and submission | Shubham | 2026-02-04 | 2026-02-07 | Done |  | 2026-02-07
Slide Deck | Prepare Slide deck | All | 2026-02-07 | 2026-02-09 | Done |  | 2026-02-11
| Review slide deck | All | 2026-02-07 | 2026-02-09 | Done |  | 2026-02-11
User Stories | Creation of User Story folder on Github | Ojas | 2026-02-07 | 2026-02-09 | Done |  | 2026-02-07
| Upload of individual Story | All | 2026-02-07 | 2026-02-09 | Done |  | 2026-02-08
(Include your expectations from project, how did you do it, which AI tool you used, what did you come to know about AI apart from the subject topic) |  |  | 2026-01-23 | 2026-02-11 | Done | Updated in the Readme file in GitHub Repo of the Project | 2026-02-11
Retrospective review |  | All | 2026-02-07 | 2026-02-10 | Done | 08-02 Sachin added the task to backlog | 2026-02-11
Presentation & Team Video Recording |  | All | 2026-02-08 | 2026-02-14 | Done |  | 2026-02-14
GitHub Finalization |  | All | 2026-02-08 | 2026-02-14 | Done |  | 2026-02-14