## Sheet1
Project 6 | Network Security Assessment of Cloud Network Architecture
Role | Responsibility | Assigned to | Sprint Start Date | Sprint End Date
Product Owner | Defines WHAT to build, prioritizes backlog, represents stakeholders. | Shubham | 2026-01-28 | 2026-02-04
Scrum Master | Facilitates process, removes blockers, coaches the team, Captures Stand Up meeting Notes | Ojas
Dev team | Self-organizing, cross-functional, delivers the increment | All
Task | Sub Task | Assigned to | Assignment Date | Due Date | Status | Status Change Comment Log | Date Of Completion
Creating Github |  | Ojas |  | 2026-01-28 | Done | 21-01 Ojas sent invite to all | 2026-01-21
| Add team members | Ojas |  | 2026-01-28 | Done |  | 2026-01-21
| Check upload/edit functions | All |  | 2026-01-28 | Done | 28-01 All other members confirmed | 2026-01-21
Updating in the Meeting Log | Daily Update capture | Ojas |  | 2026-02-02 | In Progress | Ojas is updating every alternate day
Setting Up meet |  | Ojas |  | 2026-02-28 | Done | 28-01: Due meeting notes issue in place of original google meets, Zoom is decided to be used. Ojas Created daily zoom link | 2026-01-28
Setting up Sprint Time line and Sprint Backlog Doc |  | Sachin |  | 2026-01-29 | Done | 29-01 Sachin has requested the exentsion till 4th. Yet to get confirmation . | 2026-01-30
Creation of the Project Backlog |  |  | 2026-01-28 | 2026-01-29 | In Progress
Network Architecture Review | AI-assisted research, gather sources, outline | Ojas | 2026-01-28 | 2026-01-30 | Done |  | 2026-01-30
| Write sections, create visuals, review | Ojas | 2026-01-28 | 2026-02-01 | Done | 31-01 Ojas has completed his part and uploaded his part | 2026-01-31
| Upload Prompt in Prompt folder | Ojas |  | 2026-01-31 | To Do
| Peer review | Shubham | 2026-01-28 | 2026-02-02 | To Do
Vulnerability Identification Report | AI-assisted research, gather sources, outline | Shubham | 2026-01-28 | 2026-01-30 | In Progress
| Write sections, create visuals, complete report -Review | Shubham | 2026-01-28 | 2026-02-01 | To Do
| Upload Prompt in Prompt folder | Shubham |  | 2026-01-31 | To Do
| Peer review |  | 2026-01-28 | 2026-02-02 | To be assigned
Best Practice Comparison | AI-assisted research, gather sources, outline | Nigam | 2026-01-28 | 2026-01-30 | Done | 29-01: Nigam confirmed AI research - part over | 29/02/2026
| Write sections, create visuals, review | Nigam | 2026-01-28 | 2026-02-01 | Done | 29-01: Nigam is starting now the report part. Uploaded the same. 31-01: Nigam has created report on overall basis. | 2026-01-30
| Upload Prompt in Prompt folder | Nigam |  | 2026-01-31 | To Do | 29-01 Nigam prompts are ready.
| Peer review | Sachin | 2026-01-28 | 2026-02-02 | To Do
Threat Scenario Analysis | AI-assisted research, gather sources, outline | Sachin | 2026-01-28 | 2026-01-30 | Done | 29-01 Sachin has identified few prompts, completed AI research,building the outline now. 31-01Completed threat analysis outline. | 2026-01-30
| Write sections, create visuals, review | Sachin | 2026-01-28 | 2026-02-01 | In Progress | 31-01 need to modify report in line with Network Architecture considered by Ojas
| Upload Prompt in Prompt folder | Sachin |  | 2026-01-31 | To Do
| Peer review | Ojas | 2026-01-28 | 2026-02-02 | To Do
Improvement Recommendations | AI-assisted research, gather sources, outline | All | 2026-01-28 | 2026-01-30 | In Progress | 31-01-2026 Sachin/Nigam's report/outline has improvement suggestions
| Write sections, create visuals, review | All | 2026-01-28 | 2026-02-01 | To Do
| Upload Prompt in Prompt folder | Sachin |  | 2026-01-31 | To Do
| Peer review | All | 2026-01-28 | 2026-02-02 | To be assigned
Executive Summary | Prepare final report | Sachin | 2026-01-28 | 2026-02-02 | To Do
| Team Review and checklist for the project | All | 2026-01-28 | 2026-02-03 | To Do
| Upload Prompt in Prompt folder |  |  |  | NA
| Checklist review, finalization and submission | Shubham | 2026-01-28 | 2026-02-04 | To Do
Slide Deck | Prepare Slide deck |  |  | 2026-02-04 | To be assigned
| Review slide deck | All | 2026-01-28 | 2026-02-02 | To Do
User Stories | Creation of User Story folder on Github | Ojas |  | 2026-02-04 | To Do
| Upload of individual Story | All |  | 2026-02-04 | To Do
(Include your expectations from project, how did you do it, which AI tool you used, what did you come to know about AI apart from the subject topic)
Retrospective review |  | All | 2026-01-29 | 2026-02-05 | To Do | 29-01 Sachin added the task to backlog

## Sheet2
Ojas | Done
Shubham | To Do
Nigam | In Progress
Sachin | Review
All | To be assigned
NA