## Sheet1
Project 6 | Network Security Assessment of Cloud Network Architecture
Role | Responsibility | Assigned to | Sprint Start Date | Sprint End Date
Product Owner | Defines WHAT to build, prioritizes backlog, represents stakeholders. | Shubham | 2026-01-28 | 2026-02-04
Scrum Master | Facilitates process, removes blockers, coaches the team, Captures Stand Up meeting Notes | Ojas
Dev team | Self-organizing, cross-functional, delivers the increment | All
Task | Sub Task | Assigned to | Assignment Date | Due Date | Status | Status Change Comment Log | Date Of Completion
Creating Github |  | Ojas |  | 2026-01-28 | Done | 21-01 Ojas sent invite to all | 2026-01-21
| Add team members | Ojas |  | 2026-01-28 | Done |  | 2026-01-21
| Check upload/edit functions | All |  | 2026-01-28 | Done | 28-01 All other members confirmed | 2026-01-21
Updating in the Meeting Log | Daily Update capture | Ojas |  | 2026-02-02 | In Progress | Ojas is updating every alternate day
Setting Up meet |  | Ojas |  | 2026-02-28 | In Progress | 28-01: Due meeting notes issue in place of original google meets, Zoom is decided to be used | 2026-01-25
Setting up Sprint Time line and Sprint Backlog Doc |  | Sachin |  | 2026-01-29
Check List for Peer Review | Create a Checklist to verify one's work is covers main items | Shubham |  | 2026-01-29 | To Do
Creation of the Project Backlog |  |  | 2026-01-28 | 2026-01-29 | In Progress
Network Architecture Review | AI-assisted research, gather sources, outline | Ojas | 2026-01-28 | 2026-01-30
| Write sections, create visuals, review | Ojas | 2026-01-28 | 2026-02-01 | Yes
| Upload Prompt in Prompt folder | Ojas |  | 2026-01-31
| Peer review |  | 2026-01-28 | 2026-02-02
Vulnerability Identification Report | AI-assisted research, gather sources, outline | Shubham | 2026-01-28 | 2026-01-30
| Write sections, create visuals, complete report -Review | Shubham | 2026-01-28 | 2026-02-01
| Upload Prompt in Prompt folder | Shubham |  | 2026-01-31
| Peer review |  | 2026-01-28 | 2026-02-02
Best Practice Comparison | AI-assisted research, gather sources, outline | Nigam | 2026-01-28 | 2026-01-30
| Write sections, create visuals, review | Nigam | 2026-01-28 | 2026-02-01
| Upload Prompt in Prompt folder | Nigam |  | 2026-01-31
| Peer review |  | 2026-01-28 | 2026-02-02
Threat Scenario Analysis | AI-assisted research, gather sources, outline | Sachin | 2026-01-28 | 2026-01-30
| Write sections, create visuals, review | Sachin | 2026-01-28 | 2026-02-01
| Upload Prompt in Prompt folder | Sachin |  | 2026-01-31
| Peer review |  | 2026-01-28 | 2026-02-02
Improvement Recommendations | AI-assisted research, gather sources, outline | All | 2026-01-28 | 2026-01-30
| Write sections, create visuals, review | All | 2026-01-28 | 2026-02-01
| Upload Prompt in Prompt folder | Sachin |  | 2026-01-31
| Peer review | All | 2026-01-28 | 2026-02-02
Executive Summary | Prepare final report | Sachin | 2026-01-28 | 2026-02-02
| Team Review and checklist for the project | All | 2026-01-28 | 2026-02-03
Upload Prompt in Prompt folder
| Checklist review, finalization and submission | Shubham | 2026-01-28 | 2026-02-04
Slide Deck | Prepare Slide deck |  |  | 2026-02-04
| Review slide deck | All | 2026-01-28 | 2026-02-02
User Stories | Creation of User Story folder on Github | Ojas |  | 2026-02-02
| Upload of individual Story | All |  | 2026-02-02
(Include your expectations from project, how did you do it, which AI tool you used, what did you come to know about AI apart from the subject topic)

## Sheet2
Ojas | Done
Shubham | To Do
Nigam | In Progress
Sachin | Review
All | NA